## Sheet1
Year | Quarter | Week | Backend | Testing | Difficulty
2022 | Q4 | 2022-10-11 | Create spreadsheet of project plan |  | easy
|  | 2022-10-11 | Create Trello Board |  | easy
|  | 2022-10-11 | Create Github Repo with starter code |  | easy
|  | 2022-10-11 | Setup Azure DevOps Cloud Lab |  | easy
|  | 2022-10-11 | Ensure the app runs in Cloud Shell without errors | Run flask app with prediction | medium
|  | 2022-10-11 | Create Webapp Manually |  | easy
|  | 2022-10-11 | Set up GitHub Actions |  | medium
|  | 2022-10-11 | Add the GitHub Actions badge to the README |  | easy
|  | 2022-10-11 | Test the app running in Azure App Service |  | medium
|  | 2022-10-11 | Create Azure DevOps pipeline |  | medium
|  | 2022-10-11 | Create architectural diagram |  | easy
|  | 2022-10-11 | Take screenshots demonstrating key steps |  | easy
|  | 2022-10-12 | Create README file with full instructions of how to run the code |  | easy
|  | 2022-10-12 | Create demo video and post to YouTube |  | easy
|  |  | Goals | Goals
|  |  | Submit the project | Deployed on Azure